## Detailed Work Log
Date | Time (IST) | Attribution | Work Area | Task / Feature | Work Performed | Reason | Technical Details | Outcome | Verification | Status | Evidence / Source
28-Sep-2026 | — | User-stated start; no timestamped evidence | Project history | Project start date coverage | User states JLUXE work began on 28 Sep; no accessible dated GitHub commit, project file, or other timestamped JLUXE record was found. | User explicitly required this start date; missing evidence should remain a gap rather than be inferred. | No timestamped JLUXE repository artifact identified. | Date retained explicitly as an evidence gap; no work invented. | GitHub history + accessible Project/Library search | No verified record found | Evidence & Gaps
29-Sep-2026 | 21:52 | Team — Allwin | Frontend / Architecture | Initial JLUXE frontend | Created the initial substantial Next.js public site: About, Contact, Our Work, Properties, service pages, shared header/footer, hero/services carousels, enquiry form, property listing and portfolio components. | Establish the public JLUXE site foundation. | Next.js App Router, TypeScript, Tailwind CSS; src/app/*, shared components, lib/data.ts and lib/properties.ts. | Multi-page frontend baseline entered the repository. | Commit 2937942; 4,091 insertions. | Implemented | GitHub 2937942
29-Sep-2026 | 21:56 | Team — Allwin | Git / Repository | Remote repository merge | Merged remote repository state into project history. | Align repository history. | Git merge commit 8ad6efb. | Repository history synchronized. | Commit 8ad6efb. | Completed | GitHub 8ad6efb
30-Sep-2026 | 00:28 | Team — Allwin | Backend / Database / Admin | MVP backend and admin foundation | Added Prisma schema/migration, admin auth/session/password helpers, admin pages, enquiry/property/portfolio APIs and supporting server code. | Move from frontend-only MVP toward a full-stack application. | PostgreSQL + Prisma at this stage; prisma/schema.prisma, Prisma migrations, admin routes/pages, auth/password helpers. | Core backend/auth/API/admin foundation established. | Commit f5dee7e; 6,270 additions / 641 deletions. | Implemented | GitHub f5dee7e
01-Oct-2026 | 20:44 | Dhaanush K (self) | UI/UX / Frontend | JLUXE visual refresh | Added cinematic architecture assets, hero background blending, CTA/talk button styling, premium-card hover treatment and public service/homepage refinements. | Move site toward approved premium JLUXE visual language. | Images/ and public/assets/images/; globals.css hero masks/washes/vignette, CTA/talk/premium-card styles; HeroCarousel, ServicesCarousel, service sections, SiteHeader, WorkPortfolio, PropertyListing, data. | Viridian/ivory/sand/gold visual direction established. | Commit 59f33d3; PR #2 merged. | Completed / Merged | GitHub 59f33d3 / PR #2
01-Oct-2026 | 20:44 | Dhaanush K (self) | Real Estate / Forms | Seller property submission | Added /contact/sell-property and SellPropertyForm for owners/sellers to submit property opportunities. | Provide a public seller pathway for representation, marketing or channel partnership discussions. | New sell-property page/form; property type, location, starting price, area/unit and description inputs. | Seller submission route added. | Commit 59f33d3. | Implemented / Merged | GitHub 59f33d3
01-Oct-2026 | 21:00 | Dhaanush K (self) | Deployment / Build Compatibility | Vercel-related compatibility work | Adjusted SellPropertyForm imports to use src/lib/db/types instead of generated Prisma enums; generated Prisma client artifacts were also committed. | Address deployment/build compatibility around the seller form. | Commit ce73f1b; next-env.d.ts, SellPropertyForm and src/generated/prisma/* changed/added. | Historical Vercel-oriented compatibility adjustment. | Commit ce73f1b. | Completed / Merged | GitHub ce73f1b
01-Oct-2026 | 15:48 | Team — Allwin | Database / Admin | PostgreSQL migration/admin foundation | Added SQL migration 001, pg pool/query modules and expanded admin CRUD for services, properties, portfolio and enquiries. | Establish explicit SQL/PostgreSQL access and broader admin management. | database/migrations/001_initial.sql; src/lib/db/pool.ts; src/lib/db/queries/*; admin APIs/pages. | Database-backed admin foundation expanded. | Commit 4bb12b8; PR #1 merged. | Implemented / Merged | GitHub 4bb12b8 / PR #1
02-Oct-2026 | 12:31 | Dhaanush K (self) | Admin / Media / Frontend | Media administration and service refinements | Added admin media GET/DELETE APIs, Media Library UI, media query helpers, FAQ section and service/property/work UI refinements. | Improve content-management capability and public service experiences. | Admin media routes/page/library; src/lib/db/queries/media.ts; src/lib/media.ts; service/property/work changes. | Media listing/deletion and UI refinements integrated. | Commit 0d73c3b; PR #3 merged. | Completed / Merged | GitHub 0d73c3b / PR #3
02-Oct-2026 | 15:03 | Dhaanush K (self) | Admin / Reporting | Admin controls and Excel export | Added ExcelJS and an admin enquiry export route plus broader service/property/portfolio admin controls. | Provide reporting/export capability and stronger administration. | package.json/package-lock.json; src/app/admin/api/enquiries/export/route.ts; dashboard/query/list changes. | Enquiry export and admin controls added. | Commit 3499b6f; PR #4 merged. | Completed / Merged | GitHub 3499b6f / PR #4
03-Oct-2026 | — | No verified record | Project history | Daily date coverage | No verified JLUXE-specific activity found in accessible sources. | User requested every date be considered. | No dated JLUXE GitHub commit or relevant project-library record identified. | Date retained as evidence gap. | GitHub history + accessible Library search. | No verified record found | Evidence & Gaps
04-Oct-2026 | — | No verified record | Project history | Daily date coverage | No verified JLUXE-specific activity found in accessible sources. | User requested every date be considered. | No dated JLUXE GitHub commit or relevant project-library record identified. | Date retained as evidence gap. | GitHub history + accessible Library search. | No verified record found | Evidence & Gaps
05-Oct-2026 | 16:47 | Dhaanush K (self) | Frontend / Hero | Hero carousel numbering correction | Made JLUXE intro slide unnumbered and ecosystem slides display 01–04; removed redundant bottom numbering. | Correct intended intro-plus-four-ecosystem presentation. | src/components/hero-carousel.tsx; displayIndex/displayNumber logic. | Carousel numbering matched intended sequence. | Commit 5b8aa6f; PR #8 merged. | Completed / Merged | GitHub 5b8aa6f / PR #8
05-Oct-2026 | 15:50 | Team — Allwin | UI / Mobile | Mobile UI checkpoint | Saved a checkpoint of current UI after mobile-oriented changes. | Preserve a known mobile-ready state. | Commit cd1a913; PR #6. | Mobile UI checkpoint entered main. | GitHub commit / PR history. | Completed / Merged | GitHub cd1a913 / PR #6
05-Oct-2026 | 18:20 | Dhaanush K (self) | About / Leadership | Managing Director leadership page | Added MD section to /about and dedicated /about/leadership with profile, focus areas, philosophy and vision. | Present leadership information without invented business claims. | about/leadership/page.tsx added; About page got portrait placeholder, role, tagline, biography and CTA. | Leadership route and About section integrated. | Commit ececa1a; PR #10 merged as f4deea8. | Completed / Merged | GitHub ececa1a / PR #10
05-Oct-2026 | 18:20 | Team — Allwin | Real Estate / Admin | Seller property workflow | Added seller-property API flow, enquiry status pipeline and related admin/service/property changes. | Support seller submissions and administration. | database/migrations/002_enquiry_status_pipeline.sql; /api/properties/sell; admin and seller updates. | Seller workflow entered shared application. | Commit ab7fa58; PR #11 merged. | Implemented / Merged | GitHub ab7fa58 / PR #11
05-Oct-2026 | 19:47 | Dhaanush K (self) | About / Interaction | Managing Director content slider | Replaced static MD content with three slides: Who He Is, Leadership Approach, Vision; added fixed-photo content slider, looping arrows, indicator and adaptive height. | Make MD section compact and interactive using existing information only. | src/components/managing-director-slider.tsx; About import/static-content removal; active height measurement. | Content-only slider entered main. | Commit 075fef5; PR #12 merged as 624ba27; Vercel status success. | Completed / Merged | GitHub 075fef5 / PR #12
05-Oct-2026 | Evening | Dhaanush K (self) | Debugging / Browser | React hydration mismatch investigation | Investigated data-temp-mail-org="0" appearing on enquiry email input and causing server/client attribute mismatch. | Normal browser warned; private/incognito did not. | enquiry-form.tsx was not the source of the injected attribute; Incognito removed warning. | Isolated to browser-extension DOM injection; no application workaround added. | Confirmed by normal-browser vs Incognito comparison. | Investigated / Resolved | Current conversation screenshot + Incognito test
05-Oct-2026 | Evening | Dhaanush K (self) | Git / Collaboration | Local main merge conflict recovery | Aborted a merge that conflicted in hero-carousel.tsx; created backup/main-before-sync, fetched origin and reset local main to origin/main. | Avoid losing teammate work while syncing shared branch. | Local main had 2 unique commits; origin/main had 9; backup retained 581be29; main reset to f4deea8. | Local main later reported up to date and clean. | Resolved | Current conversation Git outputs
05-Oct-2026 | After build | Dhaanush K (self) | Build / QA | Leadership build verification | Ran npm run build; Next.js 16.3.7/Turbopack compiled successfully and generated 32/32 pages. | Verify leadership route/feature build. | Routes included /about and /about/leadership; TypeScript completed successfully. | Production build passed. | Build: compiled successfully; TypeScript passed; 32/32 pages. | Verified | Current conversation build output
06-Oct-2026 | 16:42 | Team — Allwin | Real Estate / Portfolio | Property and portfolio workflow improvements | Refined public property and portfolio workflows and supporting data/UI behavior. | Improve property and Our Work flows. | Commit c090ba9; PR #13. | Workflow improvements merged. | GitHub commit / PR. | Implemented / Merged | GitHub c090ba9 / PR #13
06-Oct-2026 | 19:33 | Team — Allwin | SEO | SEO foundation | Added initial SEO foundation for public pages. | Improve metadata and crawlability. | Commit 1891bc9; PR #14. | SEO groundwork entered main. | GitHub commit / PR. | Implemented / Merged | GitHub 1891bc9 / PR #14
06-Oct-2026 | 23:08 | Team — Allwin | Media / Services / Admin | Media and service-category workflow | Added service-category migrations, media association routes and Media Library/gallery functionality. | Manage content/media relationships. | Migrations 003/004; media endpoints; gallery/admin/query updates. | Workflow merged as PR #15. | GitHub c06163f / PR #15. | Implemented / Merged | GitHub c06163f / PR #15
06-Oct-2026 | 20:16 | Team — Allwin | Branding / Assets | JLUXE favicon | Added the site favicon. | Complete branded browser identity. | Commit 9745671. | Favicon added. | GitHub commit. | Completed | GitHub 9745671
07-Oct-2026 | 17:55 | Team — Allwin | Database / Schema | Service category schema drift repair | Added migration 005_repair_service_category_schema_drift.sql. | Reconcile service-category schema differences. | Migration 005; PR #16. | Schema repair merged. | GitHub 0f11222 / PR #16. | Fixed / Merged | GitHub 0f11222 / PR #16
08-Oct-2026 | 05:16 | Team — Allwin | Media / Cloudinary | Cloudinary media workflow refinement | Refined media handling and Cloudinary configuration, including signed upload/verification/deletion paths. | Move toward managed external media storage. | src/lib/cloudinary.ts, cloudinary-client.ts, media routes and seller upload route. | Cloudinary-backed infrastructure integrated. | Commits 21706ae/d3d8187; PR #17 merged. | Implemented / Merged | GitHub 21706ae / d3d8187 / PR #17
08-Oct-2026 | 16:42 | Team — Crackthecode | Deployment / SEO | Production domain and sitemap | Changed site config and sitemap to use https://thejluxe.com. | Use production domain in public URLs. | src/lib/data.ts siteConfig.url; src/app/sitemap.ts uses it. | Production domain became source for URLs/sitemap. | Commits ebe5f7d/c1699e8; PR #18 merged. | Fixed / Merged | GitHub ebe5f7d / c1699e8 / PR #18
08-Oct-2026 | 17:22 | Team — Crackthecode | Security / Dependencies | Dependency security update | Updated dependency versions and lockfile to address security vulnerabilities. | Reduce dependency risk. | package.json + package-lock.json; PR #19. | Security update merged. | Commits a1a0d89/11fd4f5; PR #19 merged. | Fixed / Merged | GitHub a1a0d89 / 11fd4f5 / PR #19
08-Oct-2026 | 17:47 | Team — Allwin | Security / API | Persistent public API rate limiting | Added PostgreSQL-backed public API rate limits and tests for enquiry/seller-media endpoints. | Protect public endpoints from abuse. | Migration 006_public_api_rate_limits.sql; public-api-rate-limit.ts/tests; seller-rate-limit.ts. | Persistent rate limiting added. | Commit 167b0cd; PR #20 merged; Vercel status success. | Implemented / Merged | GitHub 167b0cd / PR #20
08-Oct-2026 | 17:53 | Team — Allwin | Security / API | Client fingerprint fix | Adjusted rate-limit client-key/fingerprint behavior. | Improve rate-limit identity handling. | public-api-rate-limit.ts + tests. | Fingerprint handling corrected. | Commit 2462e9c. | Fixed | GitHub 2462e9c
08-Oct-2026 | 19:41 | Team — Allwin | Frontend / Platform | JLUXE website experience finalization | Applied refinement across About, Business Solutions, Interiors & Design, service cards, header and data presentation. | Keep the platform coherent after rapid feature growth. | Commit 697a319 modified multiple public UI/data files. | Shared experience received a finalization pass. | Commit 697a319. | Implemented | GitHub 697a319
08-Oct-2026 | 20:08 | Team — Allwin | Analytics / Frontend | Google Analytics tracking | Added GA through Next.js Script afterInteractive. | Enable analytics without blocking initial render. | src/components/google-analytics.tsx; measurement ID G-SNFWGZ98QB. | Analytics instrumentation added. | Commit d4d7c71. | Implemented | GitHub d4d7c71
09-Oct-2026 | 01:19 | Team — Allwin | Email / Integrations | JLUXE enquiry email notifications | Added Resend-backed notifications for public enquiry and seller property flows. | Notify configured JLUXE recipient. | src/lib/email-notifications.ts; env-configured sender; current recipient is enquiry@thejluxe.com. | Notification integration added. | Commit fc32002; direct delivery logs unavailable. | Implemented | GitHub fc32002
09-Oct-2026 | 17:52 | Dhaanush K (self) | Frontend / Contact | Contact information and direct-contact UX | Added direct-contact panel to Contact, aligned enquiry form presentation and ignored .env.vercel.production. | Improve direct-contact UX and protect local environment file. | Commit 9078326: contact/page.tsx, enquiry-form.tsx, lib/data.ts, .gitignore. | Contact presentation improved; values later updated on 14 Oct. | PR #24 merged. | Completed / Merged | GitHub 9078326 / PR #24
09-Oct-2026 | 17:18 | Team — Allwin | Deployment / QA | Preview deployment trigger and Cloudinary import fix | Triggered fresh preview deployment and removed duplicate Cloudinary import. | Refresh preview and eliminate duplicate-import issue. | Commits 3c6152e and f06c1c2. | Preview/import cleanup entered main. | Direct Vercel logs unavailable. | Fixed / Verified | GitHub 3c6152e / f06c1c2
09-Oct-2026 | 17:22 | Team — Allwin | Visual QA | Visual stabilization | Applied another visual stabilization pass after branch synchronization. | Reduce UI regressions. | Commit 480137f; PR #22. | Visual stabilization merged. | PR #22 merged. | Completed / Merged | GitHub 480137f / PR #22
09-Oct-2026 | 19:03 | Dhaanush K (self) | Git / Collaboration | Pulled main into feature branch | Brought current main work into feature/ju's-work through shared PR workflow. | Keep feature branch synchronized. | PR #23; merge 9218b69. | Feature branch incorporated current main. | PR #23 merged. | Completed / Merged | GitHub 9218b69 / PR #23
10-Oct-2026 | — | No verified record | Project history | Daily date coverage | No verified JLUXE-specific activity found in accessible sources. | User requested every date be considered. | No dated JLUXE GitHub commit or relevant library/project record identified. | Date retained as evidence gap. | GitHub history + accessible Library search. | No verified record found | Evidence & Gaps
11-Oct-2026 | — | No verified record | Project history | Daily date coverage | No verified JLUXE-specific activity found in accessible sources. | User requested every date be considered. | No dated JLUXE GitHub commit or relevant library/project record identified. | Date retained as evidence gap. | GitHub history + accessible Library search. | No verified record found | Evidence & Gaps
12-Oct-2026 | — | No verified record | Project history | Daily date coverage | No verified JLUXE-specific activity found in accessible sources. | User requested every date be considered. | No dated JLUXE GitHub commit or relevant library/project record identified. | Date retained as evidence gap. | GitHub history + accessible Library search. | No verified record found | Evidence & Gaps
13-Oct-2026 | — | No verified record | Project history | Daily date coverage | No verified JLUXE-specific activity found in accessible sources; unrelated Library files were not used. | Avoid inferring JLUXE work from unrelated files. | No dated JLUXE GitHub commit identified. | Date retained as evidence gap. | GitHub history + accessible Library search. | No verified record found | Evidence & Gaps
14-Oct-2026 | 14:37 | Dhaanush K (self) | Real Estate / Database / API | Buyer property requirements and property enquiry workflow | Added structured buyer requirements, property-specific enquiries, migrations, forms, APIs and admin integration. | Capture buyer intent with structured requirements and property context. | Migrations 007/008/009; /contact/buy-property; /api/properties/buy; /api/properties/[slug]/enquiries; buyer-property.ts; buyer-property-enquiries.ts; enquiries.ts and property UI. | Real-estate funnel gained structured buyer/property enquiry capture. | Commit db92987; PR #25 merged; Vercel status success. | Implemented / Merged | GitHub db92987 / PR #25
14-Oct-2026 | 16:49 | Dhaanush K (self) | WhatsApp / Contact UX | Prefilled WhatsApp messages | Added contextual WhatsApp messages to header/contact/property-detail flows and updated centralized business WhatsApp configuration. | Reduce friction from website context to WhatsApp. | site-header.tsx, property-detail.tsx, contact page, lib/data.ts and enquiry query support. | WhatsApp messages now carry relevant context. | Commit 23ab8c0; PR #26 merged; Vercel status success. | Implemented / Merged | GitHub 23ab8c0 / PR #26
14-Oct-2026 | 18:20 | Team — Allwin | Deployment / Routing / Security | Admin subdomain routing | Added hostname routing so admin.thejluxe.com serves /admin and public /admin navigation can redirect to the admin subdomain. | Separate admin and public surfaces. | src/proxy.ts, next.config.ts and admin-session.ts; host-specific proxy logic. | Admin subdomain routing merged. | Commit a9a2dc0; PR #27 merged as 53acb98; Vercel status success. | Implemented / Merged | GitHub a9a2dc0 / PR #27

## Daily Summary
Date | Work Summary | Main Accomplishments | Outstanding Issues / Next Step | Overall Status | Evidence
28-Sep-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
29-Sep-2026 | Initial JLUXE frontend; Remote repository merge | Multi-page frontend baseline entered the repository.; Repository history synchronized. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub 2937942; GitHub 8ad6efb
30-Sep-2026 | MVP backend and admin foundation | Core backend/auth/API/admin foundation established. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub f5dee7e
01-Oct-2026 | JLUXE visual refresh; Seller property submission; Vercel-related compatibility work; PostgreSQL migration/admin foundation | Viridian/ivory/sand/gold visual direction established.; Seller submission route added.; Historical Vercel-oriented compatibility adjustment.; Database-backed admin foundation expanded. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub 59f33d3 / PR #2; GitHub 59f33d3; GitHub ce73f1b; GitHub 4bb12b8 / PR #1
02-Oct-2026 | Media administration and service refinements; Admin controls and Excel export | Media listing/deletion and UI refinements integrated.; Enquiry export and admin controls added. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub 0d73c3b / PR #3; GitHub 3499b6f / PR #4
03-Oct-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
04-Oct-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
05-Oct-2026 | Hero carousel numbering correction; Mobile UI checkpoint; Managing Director leadership page; Seller property workflow; Managing Director content slider; React hydration mismatch investigation; Local main merge conflict recovery; Leadership build verification | Carousel numbering matched intended sequence.; Mobile UI checkpoint entered main.; Leadership route and About section integrated.; Seller workflow entered shared application.; Content-only slider entered main. | Continue stabilization, content readiness and production verification. | Major frontend milestone | GitHub 5b8aa6f / PR #8; GitHub cd1a913 / PR #6; GitHub ececa1a / PR #10; GitHub ab7fa58 / PR #11; GitHub 075fef5 / PR #12; Current conversation screenshot + Incognito test; ; Current conversation build output
06-Oct-2026 | Property and portfolio workflow improvements; SEO foundation; Media and service-category workflow; JLUXE favicon | Workflow improvements merged.; SEO groundwork entered main.; Workflow merged as PR #15.; Favicon added. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub c090ba9 / PR #13; GitHub 1891bc9 / PR #14; GitHub c06163f / PR #15; GitHub 9745671
07-Oct-2026 | Service category schema drift repair | Schema repair merged. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub 0f11222 / PR #16
08-Oct-2026 | Cloudinary media workflow refinement; Production domain and sitemap; Dependency security update; Persistent public API rate limiting; Client fingerprint fix; JLUXE website experience finalization; Google Analytics tracking | Cloudinary-backed infrastructure integrated.; Production domain became source for URLs/sitemap.; Security update merged.; Persistent rate limiting added.; Fingerprint handling corrected. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub 21706ae / d3d8187 / PR #17; GitHub ebe5f7d / c1699e8 / PR #18; GitHub a1a0d89 / 11fd4f5 / PR #19; GitHub 167b0cd / PR #20; GitHub 2462e9c; GitHub 697a319; GitHub d4d7c71
09-Oct-2026 | JLUXE enquiry email notifications; Contact information and direct-contact UX; Preview deployment trigger and Cloudinary import fix; Visual stabilization; Pulled main into feature branch | Notification integration added.; Contact presentation improved; values later updated on 14 Oct.; Preview/import cleanup entered main.; Visual stabilization merged.; Feature branch incorporated current main. | Continue stabilization, content readiness and production verification. | Recorded activity | GitHub fc32002; GitHub 9078326 / PR #24; GitHub 3c6152e / f06c1c2; GitHub 480137f / PR #22; GitHub 9218b69 / PR #23
10-Oct-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
11-Oct-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
12-Oct-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
13-Oct-2026 | No verified JLUXE-specific activity found in accessible sources. | — | Keep as an explicit evidence gap; do not infer work. | No verified record found | Evidence & Gaps
14-Oct-2026 | Buyer property requirements and property enquiry workflow; Prefilled WhatsApp messages; Admin subdomain routing | Real-estate funnel gained structured buyer/property enquiry capture.; WhatsApp messages now carry relevant context.; Admin subdomain routing merged. | Continue production/content verification; direct Cloudflare/Vercel/Resend/Neon dashboards were not accessible. | Major real-estate + routing milestone | GitHub db92987 / PR #25; GitHub 23ab8c0 / PR #26; GitHub a9a2dc0 / PR #27

## Features and Milestones
Date / Period | Feature / Milestone | Work Area | Attribution | What Changed | Status | Primary Evidence | Caveat / Verification Note
29-Sep-2026 | Initial JLUXE frontend | Frontend / Architecture | Team — Allwin | Initial multi-page public frontend and shared components. | Implemented | GitHub 2937942 | No deployment claim.
30-Sep-2026 | MVP backend + admin | Backend / Auth / Database | Team — Allwin | Prisma schema, auth/session helpers, admin pages and public/admin APIs. | Implemented | GitHub f5dee7e | Early historical architecture used Prisma.
01-Oct-2026 | PostgreSQL migration/admin foundation | Database / Admin | Team — Allwin | SQL migration 001, pg pool/query layer and expanded admin CRUD. | Merged | GitHub 4bb12b8 / PR #1 | Prisma files remained in historical commit.
01-Oct-2026 | JLUXE visual refresh + seller submission | UI/UX / Real Estate | Dhaanush K | Cinematic visual system, CTA/talk button, premium cards, seller page/form. | Merged | GitHub 59f33d3 / PR #2 | Visual merge does not prove live production behavior.
02-Oct-2026 | Media admin + service refinements | Admin / Media / Frontend | Dhaanush K | Media API/library, FAQ and service/property/work refinements. | Merged | GitHub 0d73c3b / PR #3 | Uploads later gained Cloudinary integration.
02-Oct-2026 | Admin export | Admin / Reporting | Dhaanush K | ExcelJS enquiry export and admin controls. | Merged | GitHub 3499b6f / PR #4 | Export confirmed in code.
05-Oct-2026 | Hero carousel numbering | Frontend / UX | Dhaanush K | JLUXE intro unnumbered; ecosystem sequence 01–04. | Merged | GitHub 5b8aa6f / PR #8 | Build later passed.
05-Oct-2026 | Managing Director leadership page | About / Content | Dhaanush K | About MD section and /about/leadership profile. | Merged | GitHub ececa1a / PR #10 | Build passed.
05-Oct-2026 | Managing Director content slider | About / Interaction | Dhaanush K | Three-slide content-only slider, fixed portrait, arrows, indicator, adaptive height. | Merged | GitHub 075fef5 / PR #12 | Vercel status success on merge commit.
05-Oct-2026 | Seller property workflow | Real Estate / Admin | Team — Allwin | Seller API/status pipeline/admin improvements. | Merged | GitHub ab7fa58 / PR #11 | Expanded on 14 Oct.
06–08-Oct-2026 | Property/portfolio, SEO, media and Cloudinary | Real Estate / SEO / Media | Team — Allwin | Property/portfolio workflows, SEO foundation, service categories and Cloudinary media workflow. | Merged | GitHub c090ba9, 1891bc9, c06163f, 21706ae, d3d8187 / PRs #13–17 | Direct external-service dashboard evidence unavailable.
08-Oct-2026 | Production URL / sitemap | Deployment / SEO | Team — Crackthecode | Production domain in site config and sitemap. | Merged | GitHub ebe5f7d + c1699e8 / PR #18 | No direct Cloudflare DNS record verified.
08-Oct-2026 | Dependency security | Security | Team — Crackthecode | Dependency and lockfile security updates. | Merged | GitHub a1a0d89 + 11fd4f5 / PR #19 | Source-control evidence.
08-Oct-2026 | Public API rate limiting | Security / API | Team — Allwin | Persistent DB-backed rate limits plus fingerprint correction. | Merged | GitHub 167b0cd + 2462e9c / PR #20 | Vercel status success for PR #20 merge.
08-Oct-2026 | Google Analytics | Analytics | Team — Allwin | Next.js GA instrumentation. | Implemented | GitHub d4d7c71 | Direct Analytics dashboard evidence unavailable.
09-Oct-2026 | Resend enquiry notifications | Email / Integration | Team — Allwin | Server-side Resend notification helper and API integration. | Implemented | GitHub fc32002 | Delivery logs unavailable.
09-Oct-2026 | Contact information | Contact / UX | Dhaanush K | Direct-contact panel and contact configuration. | Merged | GitHub 9078326 / PR #24 | Values updated again on 14 Oct.
09-Oct-2026 | Preview/visual stabilization | Deployment / QA | Team — Allwin | Preview trigger, duplicate Cloudinary import fix and visual stabilization. | Merged | GitHub 3c6152e, f06c1c2, 480137f / PR #22 | No direct Vercel log export.
14-Oct-2026 | Buyer property requirements/enquiries | Real Estate / Database / API | Dhaanush K | Structured buyer requirements, property-specific enquiries, migrations and admin visibility. | Merged | GitHub db92987 / PR #25 | Vercel status success; direct live DB test unavailable.
14-Oct-2026 | WhatsApp contextual messaging | Contact / Real Estate | Dhaanush K | Prefilled messages in header/contact/property flows. | Merged | GitHub 23ab8c0 / PR #26 | Vercel status success.
14-Oct-2026 | Admin subdomain routing | Deployment / Routing / Security | Team — Allwin | admin.thejluxe.com routing plus public /admin redirects. | Merged | GitHub a9a2dc0 / PR #27; merge 53acb98 | Vercel status success; Cloudflare DNS not directly verified.

## Bugs and Fixes
Date | Bug / Issue | Area | Original Issue / Symptom | Impact | Investigation / Fix | Final Outcome | Verification | Status | Evidence / Source
01-Oct-2026 | Vercel deployment build failure | Deployment | Initial Vercel build failed because DATABASE_URL was missing. | Deployment blocked without production DB connection. | Connected Neon jluxe-production, configured production env variables and applied initial Prisma migration per handoff. | Handoff said DB/env/migration were configured but listed redeploy and production verification as the next task. | Resolved / verification incomplete | Handoff + deployment history
05-Oct-2026 | Hero carousel numbering | Frontend / UX | JLUXE intro consumed a number and bottom numbering was redundant. | Incorrect presentation sequence. | Updated hero-carousel.tsx displayIndex/displayNumber logic and removed redundant bottom numbers. | PR #8 merged; later builds succeeded. | Fixed | GitHub 5b8aa6f / PR #8
05-Oct-2026 | React hydration mismatch | Frontend / Browser | Email input showed unexpected data-temp-mail-org="0" client attribute. | Hydration warning in normal browser. | Private/incognito test removed warning; isolated to browser-extension DOM injection; no code workaround. | Confirmed locally by browser comparison. | Resolved / environment-specific | Current conversation screenshot + Incognito test
05-Oct-2026 | Main-branch merge conflict | Git / Collaboration | Local main diverged from origin/main and hero-carousel.tsx conflicted. | Risk of overwriting teammate work. | Aborted merge; created backup/main-before-sync; fetched origin; reset main to origin/main. | Subsequent status clean and synchronized. | Resolved | Current conversation Git logs/status
05-Oct-2026+ | next-env.d.ts generated churn | Build tooling | Next.js 16 changed generated references from .next/dev/types to .next/types during build. | Generated file appeared as a working-tree change. | Restored next-env.d.ts and excluded it from feature commits. | Build still passed; generated-only diff removed. | Managed / Non-blocking | Current conversation build/diff outputs

## Evidence and Gaps
Evidence / Gap | Evidence Type | Source / Record | What It Supports | Confidence | Gap / Caveat | Recommended Evidence / Action
GitHub commit history | Primary source | https://github.com/itscrackthecode/jluxe/commits/main | Exact dates/authors/files for repository activity. | High | No 28-Sep commit found. | Use as primary execution chronology.
GitHub pull requests | Primary source | https://github.com/itscrackthecode/jluxe/pulls | Confirmed PR/merge dates for #1–#27. | High | PR merge proves main integration, not complete production QA. | Use for milestone and merge status.
GitHub Vercel status checks | Deployment signal | Selected merged commit status contexts | Several merged commits reported Vercel state=success. | High for check status | No direct Vercel dashboard/log access; success status is not a full production audit. | Report as status signal only.
JLUXE_Project_Handoff_Summary.docx | Architecture / state | Library file created 01-Oct-2026 | Documents stack, DB models, APIs, auth, env vars, Neon/Vercel setup and remaining production checks. | High for handoff snapshot | Historical snapshot; later state comes from GitHub. | Use for architecture corroboration.
Continuation from 30-09-26.md | Roadmap / requirements | Library document | Describes intended phases and acceptance criteria. | Medium for planned scope | Much content is planned/future. | Do not use alone to mark completion.
Master AI specification | Requirements | JLUXE_Developers_Master_AI_Specification.md | Defines intended visual/system direction. | Low for completion | Predates requested window and is not execution proof. | Use as design intent only.
Cloudflare DNS / SSL / Turnstile | Infrastructure gap | No accessible direct dashboard/log record found | Requested by user but no verifiable completion record located. | Low / unverified | Do not mark as completed. | Add Cloudflare export/screenshots if available.
Neon production DB | Infrastructure | Handoff + Git/database history | Supports jluxe-production existence and initial migration application at handoff. | Medium-High | No direct Neon console/query logs accessible. | Do not claim production data tests without direct evidence.
Resend delivery | Email integration | GitHub fc32002 + current email-notifications.ts | Supports implementation and recipient configuration. | Medium | No delivery dashboard accessible. | Do not claim actual delivery without logs.
Browser hydration issue | Debug evidence | Current conversation screenshot + Incognito test | Supports the extension-injected attribute diagnosis. | High | Extension identity not separately verified. | Record as environment-specific.
Production verification overall | Deployment / QA | GitHub Vercel statuses + handoff | Supports repeated Vercel success signals and documented setup. | Medium | No direct live-site, Vercel, Cloudflare, Resend or Neon dashboard access. | Keep production claims conservative.
Attribution methodology | Methodology | GitHub commit authors + PR owners | Self rows use Dhaanush K evidence; team rows are labeled as team context. | High | Merge author may differ from implementer. | Do not infer ownership from merge alone.